## Sheet1
Requirements Traceability Matrix
Employee Reimbursement System
Feature/Requirment | Description(User Story) |  | Test steps(Acceptance Criteria) |  | Positive tests | Negetive tests | manual results | automated results | Overall Stauts | Assigned To
Employee login | Employees should be able login |  | link to feature file/Acceptance Criteria |  | (1.1)Scenario: Login With Correct Credentials | (1.2)Scenario: Login with incorrect credentials | 1.1 Pass, 1.2 Pass | 1.1 PASS, 1.2 fale | Incomplete | Eric Suminski
Manager login |  | Manager should be able login | link to feature file |  | (1.1)Scenario: Login With Correct Credentials | (1.2)Scenario: Login with incorrect credentials |  |  | Incomplete
Employee logout |  | Employee should be able logout |  |  | Scenario: Logout with button | Scenario: Logout button error |  |  | Incomplete
Manager logout |  | Manager should be able logout |  |  | Scenario: Logout with button | Scenario: Logout button error |  |  | Incomplete
View request |  | Manager should view request |  |  | Scenario: Table load | Scenario: Table load failed |  |  | Incomplete
Approve request |  | Manager should approve request |  |  | Scenario: Submit Approve | Scenario: Submit Approve failed |  |  | Incomplete
Deny request |  | Manager should deny request |  |  | Scenario: Submit Deny | Scenario: Submit Deny failed |  |  | Incomplete
Employee create request |  | Employee should creat request |  |  | Scenario: Create request | Scenario: request create failed |  |  | Incomplete
Employee view request |  | Employee should view request |  |  | Scenario: Table load | Scenario: Table load failed |  |  | Incomplete