## RTM
Requirement Traceability Matrix Employee Reimbursement System
Feature/Requirment | Description (User Story) | Business Rules | Positive tests | Negetive tests | manual results | automated results | Overall Status | Assigned To | Test steps (Acceptance Criteria) | notes
1. employees should be able to log in to role page and log out to login page | 1.1 requester log in to requester page |  | 1.1e: requester credentials lead to reqester page |  | success | fail | Incomplete | Quyen and Richard | ...\Project2\project2\src\test\resources\features\login.feature
|  |  | 1.1u: requester credentials validated by database |  | success |  | Incomplete
|  |  |  | 1.1s: r-credentials invalid |  |  | Incomplete
| 1.2 manager log in to manager page |  | 1.2e: correct credentials lead to manager page |  | success | success | complete
|  |  | 1.2u: manager credentials validated by database |  | success |  | Incomplete
|  |  |  | 1.1s: m-credentials invalid |  |  | Incomplete
| 1.3 requester logs out to login page |  | 1.3e: requester logs out of role page to login page |  | success
| 1.4 manager logs out to login page |  | 1.4e: manager logs out of manager page to login page |  | success
|  | BR1 usernames must be unique |  |  | success | n/a | complete |  |  | handled by primary key in database table
2. managers should view and update request status | 2.1 managers should be able to view requester requests |  | 2.1u: table loads with all requests |  | success | success | complete | Jason and Austin | \Project2\project2\src\test\resources\features\manager.feature
|  |  | 2.1e: table visible |  | success | success | complete
| 2.2 managers should be able to approve requests |  | 2.2u: request status changes from pending to approved |  | success | success | complete
| 2.3 managers should be able to deny requests |  | 2.3u: request status changes from pending to denied |  | success | success | complete
|  | BR2 status reason must not exceed 500 characters |  | 2.3s: no update if 500 characters exceeded | success | written, not tested | incomplete
3. employees should be able to create new and view their previous requests | 3.1 requesters should be able to view their previous requests |  | 3.1u: table loads with pending and previous requests |  | success |  | Incomplete | Jason and Austin | \Project2\project2\src\test\resources\features\requester.feature
|  |  | 3.1e: table visible |  | success |  | Incomplete
|  | BR3.1 requests from other users should not be visible |  | 3.1s: requests from other users visible | success |  | Incomplete
| 3.2 requesters should be able to create new requests |  | 3.2u: new requests successfully added to database |  | success |  | Incomplete
|  | BR3.2.1 request amount should not exceed 1000 |  | 3.2.1s: no submission if 1000 amount exceeded | success
|  | BR3.2.2 request reason should not exceed 500 characters |  | 3.2.2s: no submission if 500 characters exceeded | success |  | Incomplete

## project work
category | Sprint Task | Assigned to
| wireframes | richard
| acceptance criteria | austin
| feature files | richard
| RTM (this) | richard
| test plan | R, A, J, Q
| database tables | richard
| unit tests | jason, quyen
| project packages | austin, quyen
| service tests | austin
| api | quyen
| ui (web pages) | richard, jason
e2e tests
| stretch goal tests | jason
| employee controller/api | quyen
| requester webpage | austin
| manager stretch goals | richard